## Tổng quan
Chỉ số | Giá trị
Tổng số Findings | 75
CRITICAL | 29
HIGH | 23
MEDIUM | 23
Số OC | 7
Số Working Team | 7
Số Phase triển khai | 4

## OC Overview
Objective Charter | Findings | CRITICAL | Duration | Phase | Owner | Budget | Deliverables | Success Criteria | Risks
Quality Control | 21 | 7 | 12 tháng | Phase 1-4 | QC Lead | High | 20 | 11 | 4
Process QA | 6 | 5 | 12 tháng | Phase 1-4 | PQA Lead | Medium | 9 | 7 | 3
Request Fulfillment Management | 6 | 4 | 6 tháng | Phase 1-2 | ITSM Lead | Medium | 6 | 6 | 3
Incident Management | 6 | 4 | 9 tháng | Phase 1-3 | Incident Manager (new role) | Medium-High | 6 | 6 | 3
3rd Party Management | 6 | 4 | 9 tháng | Phase 1-3 | Vendor Manager | Medium | 8 | 6 | 3
Change Management | 19 | 3 | 12 tháng | Phase 1-4 | Change Manager | High | 14 | 8 | 3
Configuration Management | 11 | 2 | 9 tháng | Phase 2-4 | CMDB Manager | High (tool cost significant) | 12 | 8 | 3

## OC-Request Fulfillment Manag
Section | Content
OBJECTIVE | Thiết lập hệ thống quản lý Request Fulfillment chuyên nghiệp với metrics tracking, quality measurement và ITSM integration để nâng cao hiệu quả phục vụ người dùng
--- | ---
SCOPE - IN SCOPE
In Scope | Thiết lập metrics tracking (SLA %, cycle time)
In Scope | Xây dựng hệ thống CSAT và quality measurement
In Scope | Tích hợp ITSM automation
In Scope | Thiết lập formal service review
In Scope | Nâng cao user engagement
In Scope | Business service mapping
SCOPE - OUT OF SCOPE
Out of Scope | Service Catalog redesign toàn diện
Out of Scope | Tool replacement (nếu không cần thiết)
--- | ---
KEY DELIVERABLES
Deliverable 1 | Dashboard tracking 5 key metrics (SLA %, cycle time, backlog, resolution time, user satisfaction)
Deliverable 2 | CSAT survey process và quality metrics framework
Deliverable 3 | ITSM integration với Incident/Change/CMDB
Deliverable 4 | Monthly service review process với bottleneck analysis
Deliverable 5 | User engagement plan và communication strategy
Deliverable 6 | Business service mapping document (coverage > 75%)
--- | ---
TIMELINE
Phase | Phase 1-2
Duration | 6 tháng
Start | Tháng 1
End | Tháng 6
Milestone | T1: Setup dashboard framework
Milestone | T2: CSAT survey deployment
Milestone | T3: ITSM integration design
Milestone | T4: Pilot service review
Milestone | T5: User engagement campaign
Milestone | T6: Business service mapping hoàn thành
--- | ---
SUCCESS CRITERIA
Criteria 1 | SLA compliance rate > 90%
Criteria 2 | CSAT score > 4.0/5.0
Criteria 3 | Average cycle time giảm 20%
Criteria 4 | User engagement tăng từ 25% lên 70%
Criteria 5 | Business service mapping coverage > 75%
Criteria 6 | Monthly service review được thực hiện đúng lịch
--- | ---
STAKEHOLDERS
Sponsor | IT Director
Owner | ITSM Lead
Team | Service Desk Manager, ITSM Specialist, BI Analyst
Support | Development Team, Infrastructure Team
Customers | All end users, Business units
--- | ---
RESOURCES
Headcount | 2-3 FTE
Tools | Dashboard tool (Power BI/Grafana), Survey tool, ITSM platform
Budget | Medium
Training | ITIL Service Request Management, Metrics & Analytics
--- | ---
RISKS & MITIGATION
Risk 1 | User không tham gia CSAT survey
Risk 1 - Impact | HIGH
Risk 1 - Mitigation | Gamification, incentives, đơn giản hóa survey
Risk 2 | ITSM integration phức tạp
Risk 2 - Impact | MEDIUM
Risk 2 - Mitigation | Phân giai đoạn, pilot với scope nhỏ trước
Risk 3 | Resistance to change từ team
Risk 3 - Impact | MEDIUM
Risk 3 - Mitigation | Training, communication, involve team sớm

## OC-Incident Management
Section | Content
OBJECTIVE | Xây dựng quy trình Incident Management tuân thủ ITIL/ISO với SLA rõ ràng, escalation formal và automation để giảm MTTR và nâng cao user satisfaction
--- | ---
SCOPE - IN SCOPE
In Scope | Định nghĩa và gán Incident Manager role
In Scope | Thiết lập SLA theo severity (P1-P4)
In Scope | Xây dựng escalation path formal
In Scope | Workflow automation
In Scope | ITSM integration (Problem/Change/CMDB)
In Scope | ITIL/ISO compliance implementation
SCOPE - OUT OF SCOPE
Out of Scope | Major Incident Management (sẽ làm giai đoạn sau)
Out of Scope | Service Desk restructuring
--- | ---
KEY DELIVERABLES
Deliverable 1 | Incident Manager role definition và assignment
Deliverable 2 | SLA document đã được phê duyệt (P1: 4h, P2: 8h, P3: 24h, P4: 72h)
Deliverable 3 | Escalation matrix theo severity và technical domain
Deliverable 4 | Automated incident creation và assignment workflow
Deliverable 5 | Incident-Problem-Change-CMDB integration
Deliverable 6 | ITIL compliance assessment report
--- | ---
TIMELINE
Phase | Phase 1-3
Duration | 9 tháng
Start | Tháng 1
End | Tháng 9
Milestone | T1: Role definition, SLA approval
Milestone | T2: Escalation matrix deployment
Milestone | T3: Automation pilot (auto-create, auto-assign)
Milestone | T6: ITSM integration implementation
Milestone | T9: ITIL compliance audit
--- | ---
SUCCESS CRITERIA
Criteria 1 | P1 MTTR < 4 giờ (compliance > 95%)
Criteria 2 | P2 MTTR < 8 giờ (compliance > 90%)
Criteria 3 | Escalation compliance > 95%
Criteria 4 | Automation rate > 60% (create, assign, categorize)
Criteria 5 | Incident-CMDB linkage > 80%
Criteria 6 | ITIL compliance score > 85%
--- | ---
STAKEHOLDERS
Sponsor | IT Director
Owner | Incident Manager (new role)
Team | Service Desk Team, ITSM Specialist, Technical Support
Support | Development Team, Infrastructure Team, DevOps
Customers | All end users
--- | ---
RESOURCES
Headcount | 1 Incident Manager + 3-5 support staff
Tools | ITSM platform với automation, Monitoring tools integration, CMDB
Budget | Medium-High
Training | ITIL Incident Management, Automation tools, ITSM platform
--- | ---
RISKS & MITIGATION
Risk 1 | Incident Manager role không được chấp nhận bởi team
Risk 1 - Impact | HIGH
Risk 1 - Mitigation | Clear role definition, authority, training, management support
Risk 2 | SLA quá aggressive, không đạt được
Risk 2 - Impact | HIGH
Risk 2 - Mitigation | Baseline measurement trước, SLA realistic dựa trên data
Risk 3 | Automation gây lỗi hoặc mis-assignment
Risk 3 - Impact | MEDIUM
Risk 3 - Mitigation | Pilot kỹ, có manual fallback, continuous tuning

## OC-Change Management
Section | Content
OBJECTIVE | Nâng cao Change Management từ ad-hoc lên process maturity level 3-4 với risk-based approach, formal governance, automation và compliance tracking
--- | ---
SCOPE - IN SCOPE
In Scope | Risk assessment framework và classification
In Scope | Backup và retention policy
In Scope | Audit process cho CM
In Scope | CR template optimization
In Scope | Communication plan
In Scope | CAB governance
In Scope | RACI documentation
In Scope | CFR root cause analysis
In Scope | Incident-Change linkage
In Scope | CMDB integration
In Scope | PIR automation
In Scope | Maintenance window policy
In Scope | Change freeze periods
In Scope | Training và certification
SCOPE - OUT OF SCOPE
Out of Scope | Emergency change process redesign (Phase 2)
Out of Scope | Standard change automation toàn diện (Phase 3)
--- | ---
KEY DELIVERABLES
Deliverable 1 | Risk assessment framework (scale 1-5) với escalation paths
Deliverable 2 | Data retention policy (1-3-5 năm theo tier) và backup procedure
Deliverable 3 | CM audit schedule và compliance checklist
Deliverable 4 | Simplified CR templates (3 loại: Standard, Normal, Emergency)
Deliverable 5 | Communication plan framework (pre/during/post-change)
Deliverable 6 | CAB charter với decision criteria và meeting cadence
Deliverable 7 | RACI matrix formal document
Deliverable 8 | CFR analysis process và improvement backlog
Deliverable 9 | Automated Incident-Change linkage
Deliverable 10 | CMDB integration for change impact analysis
Deliverable 11 | CI/CD integrated PIR checks
Deliverable 12 | Criticality-based maintenance windows
Deliverable 13 | Change freeze calendar
Deliverable 14 | CM training program và certification requirements
--- | ---
TIMELINE
Phase | Phase 1-4
Duration | 12 tháng
Start | Tháng 1
End | Tháng 12
Milestone | T1: Risk framework, RACI
Milestone | T3: CAB governance, templates
Milestone | T6: CMDB integration, communication plan
Milestone | T9: PIR automation, maintenance windows
Milestone | T12: Training program, compliance audit
--- | ---
SUCCESS CRITERIA
Criteria 1 | Change success rate > 95%
Criteria 2 | Emergency changes < 10% of total
Criteria 3 | CAB attendance > 80%
Criteria 4 | PIR completion rate > 90%
Criteria 5 | CMDB linkage > 85%
Criteria 6 | Change-related incidents giảm 30%
Criteria 7 | Audit compliance score > 90%
Criteria 8 | Team CM certification > 70%
--- | ---
STAKEHOLDERS
Sponsor | CTO
Owner | Change Manager
Team | Change Management Team, CAB Members, PQA
Support | Development Team, DevOps, Infrastructure, Product Team
Customers | All technical teams, Business stakeholders
--- | ---
RESOURCES
Headcount | 2-3 Change Coordinators + CAB members (part-time)
Tools | ITSM platform, CMDB, CI/CD integration, Dashboard/BI
Budget | High
Training | ITIL Change Management, Risk Management, CAB leadership
--- | ---
RISKS & MITIGATION
Risk 1 | CAB meetings quá nhiều, impact productivity
Risk 1 - Impact | MEDIUM
Risk 1 - Mitigation | Pre-screening, batch approval, emergency CAB only khi cần
Risk 2 | Risk assessment subjective, không consistent
Risk 2 - Impact | HIGH
Risk 2 - Mitigation | Clear criteria, training, regular calibration
Risk 3 | CMDB data không accurate, impact analysis sai
Risk 3 - Impact | HIGH
Risk 3 - Mitigation | CMDB accuracy improvement parallel, validation process

## OC-Configuration Management
Section | Content
OBJECTIVE | Triển khai CMDB chuyên nghiệp thay thế Excel, với formal policy, automated discovery, relationship mapping và integration với ITSM processes
--- | ---
SCOPE - IN SCOPE
In Scope | CMDB policy formal
In Scope | CMDB tool selection và implementation
In Scope | CI relationship và service dependency mapping
In Scope | Audit trail và audit process
In Scope | CI ownership assignment
In Scope | CMDB Steward role và governance
In Scope | Integration với Incident và Change
In Scope | Data quality standards
In Scope | Auto-population từ monitoring tools
In Scope | CMDB team training
In Scope | CMDB effectiveness KPIs
SCOPE - OUT OF SCOPE
Out of Scope | Full enterprise architecture modeling (giai đoạn sau)
Out of Scope | Financial asset management integration (nếu cần tool khác)
--- | ---
KEY DELIVERABLES
Deliverable 1 | CMDB policy document đã được phê duyệt
Deliverable 2 | CMDB tool implementation (ServiceNow/Jira/iTop/...)
Deliverable 3 | CI classification schema và relationship types
Deliverable 4 | CI relationship map cho top 20 critical services
Deliverable 5 | Audit process và quarterly audit schedule
Deliverable 6 | CI ownership matrix (100% coverage)
Deliverable 7 | CMDB Steward role definition và assignment
Deliverable 8 | IM-CM-CMDB integration
Deliverable 9 | Data quality standards document (accuracy > 95%)
Deliverable 10 | Automated discovery implementation (servers, network, cloud)
Deliverable 11 | CMDB training program
Deliverable 12 | CMDB dashboard với effectiveness KPIs
--- | ---
TIMELINE
Phase | Phase 2-4
Duration | 9 tháng
Start | Tháng 4
End | Tháng 12
Milestone | T4: Policy approval, tool selection
Milestone | T5: Tool implementation, initial data load
Milestone | T6: Relationship mapping pilot
Milestone | T7: IM-CM integration
Milestone | T9: Auto-discovery deployment
Milestone | T12: Full production, KPI tracking
--- | ---
SUCCESS CRITERIA
Criteria 1 | CMDB accuracy > 95%
Criteria 2 | CI coverage > 90% (critical infrastructure)
Criteria 3 | Relationship accuracy > 90%
Criteria 4 | CI update timeliness < 24h
Criteria 5 | Incident-CMDB linkage > 80%
Criteria 6 | Change-CMDB impact analysis usage > 85%
Criteria 7 | Auto-discovery coverage > 70%
Criteria 8 | Audit compliance > 95%
--- | ---
STAKEHOLDERS
Sponsor | CTO
Owner | CMDB Manager
Team | Configuration Analysts (2-3), CMDB Steward
Support | All technical teams, Infrastructure, DevOps, Security
Customers | Incident Management, Change Management, Problem Management
--- | ---
RESOURCES
Headcount | 2-3 Configuration Analysts full-time
Tools | CMDB tool license, Discovery tools, Integration adapters
Budget | High (tool cost significant)
Training | CMDB best practices, Tool-specific training, ITIL Configuration Management
--- | ---
RISKS & MITIGATION
Risk 1 | Tool selection sai, không meet requirements
Risk 1 - Impact | CRITICAL
Risk 1 - Mitigation | Thorough RFP, POC với 2-3 vendors, stakeholder review
Risk 2 | Data migration từ Excel phức tạp, nhiều lỗi
Risk 2 - Impact | HIGH
Risk 2 - Mitigation | Data cleansing trước, phân giai đoạn, validation process
Risk 3 | Technical teams không update CMDB
Risk 3 - Impact | HIGH
Risk 3 - Mitigation | Integration với automation tools, enforcement policy, metrics

## OC-Process QA
Section | Content
OBJECTIVE | Xây dựng Process QA function từ 0 với systematic audit approach, coverage expansion và continuous improvement để đảm bảo ITSM compliance và maturity
--- | ---
SCOPE - IN SCOPE
In Scope | Audit checklists cho IM, CM, PM
In Scope | Audit frequency tăng từ yearly lên quarterly
In Scope | Coverage expansion từ 3% lên 50%
In Scope | Metrics framework (target > 80%)
In Scope | Escalation process cho critical findings
In Scope | Maturity assessment framework
SCOPE - OUT OF SCOPE
Out of Scope | Code quality audit (thuộc QC team)
Out of Scope | Security audit (thuộc Security team)
--- | ---
KEY DELIVERABLES
Deliverable 1 | Audit checklists cho 10 ITSM processes (IM, CM, PM, RFC, CMDB, SLM, etc.)
Deliverable 2 | Quarterly audit schedule và plan
Deliverable 3 | Process coverage roadmap (Year 1: 30%, Year 2: 50%)
Deliverable 4 | Metrics tracking framework (10+ KPIs per process)
Deliverable 5 | Escalation matrix cho findings (Critical < 7 days, High < 30 days)
Deliverable 6 | Process maturity assessment model (Level 1-5)
Deliverable 7 | Audit report templates
Deliverable 8 | Findings tracking và remediation dashboard
Deliverable 9 | Compliance scorecard
--- | ---
TIMELINE
Phase | Phase 1-4
Duration | 12 tháng
Start | Tháng 1
End | Tháng 12
Milestone | T1: Checklists, escalation process
Milestone | T3: Q1 audit (IM, CM, PM)
Milestone | T6: Q2 audit (expand 3 processes)
Milestone | T9: Q3 audit, maturity assessment
Milestone | T12: Q4 audit, annual compliance report
--- | ---
SUCCESS CRITERIA
Criteria 1 | Audit coverage > 30% (Year 1)
Criteria 2 | Quarterly audit on-time completion > 95%
Criteria 3 | Critical findings resolution < 7 days: 100%
Criteria 4 | High findings resolution < 30 days: > 90%
Criteria 5 | Process compliance average score > 85%
Criteria 6 | Metrics tracking > 80% coverage
Criteria 7 | Maturity level tăng từ 2 lên 3 (average)
--- | ---
STAKEHOLDERS
Sponsor | IT Director
Owner | PQA Lead
Team | Process Auditors (2), Compliance Specialist
Support | All process owners
Customers | Management, Process owners, Audit/Compliance committee
--- | ---
RESOURCES
Headcount | 2-3 PQA specialists
Tools | GRC tool (optional), Audit management platform, Dashboard
Budget | Medium
Training | ITIL, ISO 20000, Audit methodology
--- | ---
RISKS & MITIGATION
Risk 1 | Process owners resist audit, không cooperate
Risk 1 - Impact | HIGH
Risk 1 - Mitigation | Position audit as help not blame, management support, collaborative approach
Risk 2 | PQA team thiếu technical knowledge
Risk 2 - Impact | MEDIUM
Risk 2 - Mitigation | Hire experienced auditors, continuous training, SME support
Risk 3 | Findings không được remediate
Risk 3 - Impact | HIGH
Risk 3 - Mitigation | Clear escalation, management visibility, track in KPIs

## OC-3rd Party Management
Section | Content
OBJECTIVE | Thiết lập formal 3rd Party Management framework với vendor governance, SLA monitoring, risk assessment và performance tracking
--- | ---
SCOPE - IN SCOPE
In Scope | 3PM Policy formal
In Scope | Vendor classification (criticality, spend, risk)
In Scope | SLA monitoring process
In Scope | Vendor performance metrics
In Scope | Risk assessment framework
In Scope | Roles & authority definition
SCOPE - OUT OF SCOPE
Out of Scope | Contract negotiation (thuộc Procurement)
Out of Scope | Vendor onboarding process (giai đoạn sau)
--- | ---
KEY DELIVERABLES
Deliverable 1 | 3PM Policy document đã được phê duyệt
Deliverable 2 | Vendor classification matrix (Tier 1/2/3)
Deliverable 3 | Vendor inventory database (tất cả vendors hiện tại)
Deliverable 4 | SLA monitoring dashboard
Deliverable 5 | Vendor performance scorecard (monthly)
Deliverable 6 | Risk assessment templates và register
Deliverable 7 | RACI matrix cho 3PM activities
Deliverable 8 | Vendor review process (quarterly for Tier 1, biannual for Tier 2)
--- | ---
TIMELINE
Phase | Phase 1-3
Duration | 9 tháng
Start | Tháng 1
End | Tháng 9
Milestone | T1: Policy draft, vendor inventory
Milestone | T2: Classification complete
Milestone | T3: SLA monitoring pilot (Tier 1)
Milestone | T6: Full SLA monitoring, risk assessment
Milestone | T9: Performance tracking, quarterly reviews
--- | ---
SUCCESS CRITERIA
Criteria 1 | 100% vendors được classify
Criteria 2 | SLA compliance Tier 1 vendors > 95%
Criteria 3 | Vendor performance review on-time > 90%
Criteria 4 | High-risk vendors có mitigation plan: 100%
Criteria 5 | Vendor-related incidents giảm 25%
Criteria 6 | Contract renewal process improvement (lead time -30%)
--- | ---
STAKEHOLDERS
Sponsor | CFO / CTO
Owner | Vendor Manager
Team | Contract Specialist, ITSM Lead
Support | Procurement, Legal, Finance, Technical teams
Customers | All teams sử dụng vendor services
--- | ---
RESOURCES
Headcount | 1-2 Vendor Managers
Tools | Vendor management platform, Contract repository, Dashboard
Budget | Medium
Training | Vendor management best practices, Contract management, Risk assessment
--- | ---
RISKS & MITIGATION
Risk 1 | Vendors không provide SLA data
Risk 1 - Impact | HIGH
Risk 1 - Mitigation | Contract clause yêu cầu reporting, escalation process
Risk 2 | Vendor classification subjective
Risk 2 - Impact | MEDIUM
Risk 2 - Mitigation | Clear criteria (spend, criticality, replaceability), stakeholder review
Risk 3 | Resource constraints - too many vendors
Risk 3 - Impact | MEDIUM
Risk 3 - Mitigation | Prioritize Tier 1, consolidate vendors nếu có thể

## OC-Quality Control
Section | Content
OBJECTIVE | Transform QC function từ ad-hoc thành systematic approach với QC strategy, test automation, metrics-driven và compliance với international standards
--- | ---
SCOPE - IN SCOPE
In Scope | QC strategy và roadmap
In Scope | Test planning process standardization
In Scope | QA/QC metrics và KPIs
In Scope | Test coverage measurement
In Scope | Test automation strategy
In Scope | Test data management
In Scope | International standards compliance (ISO 29119, ISTQB)
In Scope | Defect management process
In Scope | Quality gates enforcement
In Scope | Test environment management
In Scope | QC policy update
In Scope | RACI documentation
In Scope | Regression testing process
In Scope | Performance testing benchmarks
In Scope | Training program
In Scope | Defect triage process
In Scope | Test execution reports
In Scope | Automation tools training
In Scope | Release testing process
In Scope | Continuous improvement framework
In Scope | GDPR compliance trong testing
SCOPE - OUT OF SCOPE
Out of Scope | Full shift-left testing transformation (Phase 2)
Out of Scope | Production monitoring (thuộc DevOps)
--- | ---
KEY DELIVERABLES
Deliverable 1 | QC Strategy document (3-year roadmap)
Deliverable 2 | Standardized test planning templates
Deliverable 3 | QC metrics dashboard (15+ KPIs)
Deliverable 4 | Test coverage tool và target (>80%)
Deliverable 5 | Test automation framework và strategy (target 60% automation Year 1)
Deliverable 6 | Test data management process và tool
Deliverable 7 | ISO 29119 compliance gap analysis và roadmap
Deliverable 8 | Defect management workflow trong ITSM
Deliverable 9 | Quality gates checklist (6 gates từ requirements → production)
Deliverable 10 | Test environment configuration management
Deliverable 11 | QC Policy v2.0
Deliverable 12 | RACI matrix cho QC activities
Deliverable 13 | Automated regression test suite
Deliverable 14 | Performance testing baseline và benchmarks
Deliverable 15 | QC training program (automation, performance, security testing)
Deliverable 16 | Weekly defect triage process
Deliverable 17 | Automated test execution reports
Deliverable 18 | Release testing checklist và rollback plans
Deliverable 19 | Quarterly continuous improvement review process
Deliverable 20 | GDPR compliance testing guidelines
--- | ---
TIMELINE
Phase | Phase 1-4
Duration | 12 tháng
Start | Tháng 1
End | Tháng 12
Milestone | T1-3: Strategy, metrics, test planning (Phase 1)
Milestone | T4-6: Test coverage, automation framework (Phase 2)
Milestone | T7-9: Automation implementation, performance testing (Phase 3)
Milestone | T10-12: Compliance, continuous improvement (Phase 4)
--- | ---
SUCCESS CRITERIA
Criteria 1 | Test coverage > 80%
Criteria 2 | Test automation coverage > 60%
Criteria 3 | Defect leakage to production < 5%
Criteria 4 | Test execution efficiency > 90%
Criteria 5 | Regression testing automation > 80%
Criteria 6 | Performance baseline established cho 100% critical flows
Criteria 7 | QC team automation skill từ 25% lên 70%
Criteria 8 | ISO 29119 compliance gap < 20%
Criteria 9 | Quality gate compliance > 90%
Criteria 10 | Test environment availability > 95%
Criteria 11 | GDPR compliance testing: 100% cho PII-related features
--- | ---
STAKEHOLDERS
Sponsor | CTO / VP Engineering
Owner | QC Lead
Team | Test Engineers (5-8), Automation Engineers (2-3)
Support | Development Team, DevOps, Product Team, Security Team
Customers | End users, Product Management, Business stakeholders
--- | ---
RESOURCES
Headcount | 5-8 QC engineers (2-3 automation specialists)
Tools | Test management tool, Automation framework (Selenium/Playwright/etc), Performance testing (JMeter/Gatling), Test data management tool, Code coverage tool
Budget | High
Training | Test automation, Performance testing, Security testing, ISTQB certification
--- | ---
RISKS & MITIGATION
Risk 1 | Automation skill gap lớn (current 25-30%)
Risk 1 - Impact | CRITICAL
Risk 1 - Mitigation | Intensive training program, hire automation experts, external consultants
Risk 2 | Chỉ 1 test environment - bottleneck và conflicts
Risk 2 - Impact | HIGH
Risk 2 - Mitigation | Setup thêm environments, containerization, environment booking system
Risk 3 | Development team resistance to quality gates
Risk 3 - Impact | MEDIUM
Risk 3 - Mitigation | Clear communication, gradual enforcement, management support
Risk 4 | Test data management phức tạp (GDPR, PII)
Risk 4 - Impact | HIGH
Risk 4 - Mitigation | Data masking tools, synthetic data generation, legal review

## Phân bố theo lĩnh vực
Lĩnh vực | Số lượng Findings | Tỷ lệ %
QC | 21 | 28
Change Management | 19 | 25.3
Configuration | 11 | 14.7
Request fullfilment Management | 6 | 8
Incident | 6 | 8
Process QA | 6 | 8
3rd party Management | 6 | 8

## Working Teams
Working Team | Team Lead | Thành viên | Hỗ trợ | Số Findings | Số CRITICAL
Quality Control | QC/QA Team | QC Lead, Test Engineers, Automation Engineers | Development Team, DevOps Team | 21 | 7
Process QA | Process Quality Assurance Team | PQA Lead, Process Auditors | All process owners | 6 | 5
Request Fulfillment Management | ITSM Core Team | ITSM Lead, Service Desk Manager, BI Team | Development Team, Infrastructure Team | 6 | 4
Incident Management | ITSM Core Team | Incident Manager (new role), ITSM Specialist, Service Desk Team | Development Team, Infrastructure Team | 6 | 4
3rd Party Management | Vendor Management Team | Vendor Manager, Contract Specialist, ITSM Lead | Legal, Finance, Technical Teams | 6 | 4
Change Management | Change Management Team | Change Manager, CAB Members, PQA | Development Team, DevOps Team, Infrastructure | 19 | 3
Configuration Management | Configuration Management Team | CMDB Manager, Configuration Analysts | All technical teams | 11 | 2

## Phase 1
Area | Task | Owner | Priority
ITSM Governance | Xác định và gán Incident Manager role | ITSM Core Team + CAB | CRITICAL
ITSM Governance | Thiết lập SLA cho Incident (P1-P4) | ITSM Core Team + CAB | CRITICAL
ITSM Governance | Thiết lập escalation matrix | ITSM Core Team + CAB | CRITICAL
ITSM Governance | Xây dựng Change risk assessment framework | ITSM Core Team + CAB | CRITICAL
ITSM Governance | Thiết lập RACI matrix cho tất cả quy trình | ITSM Core Team + CAB | CRITICAL
Process QA - Khởi động | Tạo audit checklists cho IM, CM, PM | PQA Team | CRITICAL
Process QA - Khởi động | Lên lịch audit quarterly thay vì yearly | PQA Team | CRITICAL
Process QA - Khởi động | Thiết lập escalation path cho critical findings | PQA Team | CRITICAL
3rd Party Management - Cơ bản | Tạo 3PM Policy formal | Vendor Management Team | CRITICAL
3rd Party Management - Cơ bản | Phân loại vendors theo criticality | Vendor Management Team | CRITICAL
3rd Party Management - Cơ bản | Thiết lập SLA monitoring cơ bản | Vendor Management Team | CRITICAL

## Phase 2
Area | Task | Owner | Priority
Configuration Management | Thiết lập CMDB policy formal | Configuration Management Team | CRITICAL → HIGH
Configuration Management | Đánh giá và chọn CMDB tool (thay Excel) | Configuration Management Team | CRITICAL → HIGH
Configuration Management | Map CI relationships & service dependencies | Configuration Management Team | CRITICAL → HIGH
Configuration Management | Thiết lập CI ownership và CMDB Steward role | Configuration Management Team | CRITICAL → HIGH
Configuration Management | Integrate CMDB với Incident và Change | Configuration Management Team | CRITICAL → HIGH
Change Management - Nâng cao | Thiết lập backup và retention policy cho CR | Change Management Team + CAB | CRITICAL → HIGH
Change Management - Nâng cao | Đơn giản hóa CR template theo loại | Change Management Team + CAB | CRITICAL → HIGH
Change Management - Nâng cao | Thiết lập Communication Plan chi tiết | Change Management Team + CAB | CRITICAL → HIGH
Change Management - Nâng cao | Xây dựng CAB decision criteria và lịch họp | Change Management Team + CAB | CRITICAL → HIGH
Change Management - Nâng cao | Implement Incident-Change linkage | Change Management Team + CAB | CRITICAL → HIGH
Request Fulfillment - Metrics | Setup dashboard tracking SLA %, cycle time | ITSM Core Team + BI Team | CRITICAL → HIGH
Request Fulfillment - Metrics | Thiết lập CSAT survey và quality metrics | ITSM Core Team + BI Team | CRITICAL → HIGH
Request Fulfillment - Metrics | Map requests to business services | ITSM Core Team + BI Team | CRITICAL → HIGH
QC - Foundation | Xây dựng QC strategy và roadmap | QC/QA Team | CRITICAL
QC - Foundation | Chuẩn hóa test planning process | QC/QA Team | CRITICAL
QC - Foundation | Thiết lập QA/QC metrics và KPIs | QC/QA Team | CRITICAL
QC - Foundation | Thiết lập test coverage measurement | QC/QA Team | CRITICAL

## Phase 3
Area | Task | Owner | Priority
Workflow Automation | Tự động hóa incident creation và assignment | DevOps Team + ITSM Core Team | HIGH
Workflow Automation | Tự động hóa ITSM integration (IM-CM-PM-CMDB) | DevOps Team + ITSM Core Team | HIGH
Workflow Automation | Setup auto-population CMDB từ monitoring tools | DevOps Team + ITSM Core Team | HIGH
Workflow Automation | Tự động hóa PIR check với CI/CD | DevOps Team + ITSM Core Team | HIGH
QC Automation | Xây dựng test automation strategy | QC/QA Team + DevOps | CRITICAL → HIGH
QC Automation | Setup test data management process | QC/QA Team + DevOps | CRITICAL → HIGH
QC Automation | Implement automated regression testing | QC/QA Team + DevOps | CRITICAL → HIGH
QC Automation | Training automation tools cho team (hiện tại 25-30%) | QC/QA Team + DevOps | CRITICAL → HIGH
Change Management - Advanced | Implement batch approval cho related changes | Change Management Team + DevOps | MEDIUM
Change Management - Advanced | Thiết lập maintenance window based on criticality | Change Management Team + DevOps | MEDIUM
Change Management - Advanced | Định nghĩa change freeze periods | Change Management Team + DevOps | MEDIUM
Change Management - Advanced | Auto dashboard data refresh | Change Management Team + DevOps | MEDIUM

## Phase 4
Area | Task | Owner | Priority
Compliance & Standards | Implement ITIL/ISO compliance cho Incident Management | PQA Team + ITSM Lead | HIGH → MEDIUM
Compliance & Standards | QC compliance với chuẩn quốc tế (ISO 29119, ISTQB) | PQA Team + ITSM Lead | HIGH → MEDIUM
Compliance & Standards | GDPR và data protection trong testing | PQA Team + ITSM Lead | HIGH → MEDIUM
Compliance & Standards | Setup CM audit schedule và compliance tracking | PQA Team + ITSM Lead | HIGH → MEDIUM
Process Maturity Assessment | Conduct maturity assessment cho tất cả quy trình | PQA Team + Process Owners | CRITICAL → MEDIUM
Process Maturity Assessment | Expand audit coverage từ 3% lên 30-50% | PQA Team + Process Owners | CRITICAL → MEDIUM
Process Maturity Assessment | Setup process improvement backlog | PQA Team + Process Owners | CRITICAL → MEDIUM
Process Maturity Assessment | Analyze change failure root causes strategically | PQA Team + Process Owners | CRITICAL → MEDIUM
Training & Capability Building | Xây dựng CM training chuyên sâu và đặc thù | ITSM Lead + L&D + HR | MEDIUM
Training & Capability Building | Định nghĩa certification requirements cho CM | ITSM Lead + L&D + HR | MEDIUM
Training & Capability Building | QC skill gap training và capability roadmap | ITSM Lead + L&D + HR | MEDIUM
Training & Capability Building | CMDB training cho all technical teams | ITSM Lead + L&D + HR | MEDIUM
Advanced Analytics & Reporting | Setup KPI đo CMDB effectiveness | BI Team + All Process Owners | MEDIUM
Advanced Analytics & Reporting | Vendor metrics và performance tracking | BI Team + All Process Owners | MEDIUM
Advanced Analytics & Reporting | Test execution reports và analytics | BI Team + All Process Owners | MEDIUM
Advanced Analytics & Reporting | Continuous improvement metrics dashboard | BI Team + All Process Owners | MEDIUM

## All Findings
STT | Area | Finding | Priority | Impact | Action | Owner
1 | Request fullfilment Management | Metrics not tracked (SLA %, cycle time) | CRITICAL | Cannot measure performance, justify resources | Setup dashboard tracking 5 key metrics
2 | Request fullfilment Management | NO quality & CSAT measurement | CRITICAL | Don't know if users happy or quality good | Create CSAT survey, quality metrics
3 | Request fullfilment Management | Weak ITSM integration (all manual) | CRITICAL | Cannot do impact analysis, leverage data | Auto-link incidents/changes, CMDB update
4 | Request fullfilment Management | NO formal service review | CRITICAL | Problems repeat, trends not identified | Setup monthly review with bottleneck analysis
5 | Request fullfilment Management | Weak user engagement (25%) | HIGH | Users don't know SLA, no feedback channel | Communicate SLA clearly, setup feedback
6 | Request fullfilment Management | NO business service mapping (25%) | HIGH | Cannot prioritize by business impact | Map requests to services, improve prioritization
7 | Incident | Incident Manager role not defined | CRITICAL | No one owns IM quality | Define & assign Incident Manager role + responsibilities
8 | Incident | SLA not approved per severity (P1-P4) | CRITICAL | No resolution target → cannot measure performance | Define SLA per severity, get approval
9 | Incident | Escalation path ad-hoc, not formal | CRITICAL | Incidents escalate slowly → delayed resolution | Create escalation matrix by severity/type
10 | Incident | Workflow automation 0% - all manual | HIGH | Manual work = 80% admin time → slow response | Setup auto incident creation, auto-assign, priority
11 | Incident | ITSM integration 0% (Problem/Change/CMDB) | CRITICAL | Cannot do impact analysis → wrong decisions | Integrate incidents with Problem/Change/CMDB
12 | Incident | ITIL/ISO compliance 0% | HIGH | Not industry standard → audit risk | Implement ITIL IM practices, plan audit
13 | Change Management | Phân tích rủi ro chưa có thang đánh giá và phân loại | CRITICAL | Không phân loại mức rủi ro, không có escalation path, tất cả đều theo luồng chung nên có thể sẽ bị chậm do không có đánh giấu ưu tiên | - Tạo thang đánh giá rủi ro 1-5 - Xác định các tiêu chí thay đổi cao rủi ro - Tạo đường dẫn escalation (escalation path) - Ghi nhận thành tài liệu | Change Management, CAB team, PQA
14 | Change Management | Chưa có quy định về lưu trữ và backup dữ liệu CR | CRITICAL | - Không biết thời gian lưu giữ dữ liệu RFC - Không có Kế hoạch khôi phục khi xảy ra sự cố (DR) - Mất khả năng truy vết lịch sử thay đổi (traceability) | - Định rõ chính sách lưu giữ (thời hạn lưu trữ, theo iTIL thì 1-3-5 năm tùy theo Tier, ISO 27001: 5 năm) - Tạo quy trình sao lưu hàng tháng - Test quy trình khôi phục (restore) | Change Management, Infra
15 | Change Management | Chưa triển khai Audit đối với hoạt động CM | CRITICAL | Không track được tuân thủ với chính sách, không đánh giá được các rủi ro vi phạm và có | - Lên lịch compliance audit - Xác định phạm vi audit & danh sách kiểm tra (checklist) - Ghi lại các vi phạm & Kế hoạch khắc phục | Change Management, PQA
16 | Change Management | CR template quá dài, nhiều thông tin chưa có cơ chế đánh giá, xác thực (ví dụ: Đánh giá ảnh hưởng, đánh giá rủi ro…) | HIGH | Khó khăn cho người tạo CR và review/phê duyệt CR | - Đơn giản hóa template theo loại CR - Bổ sung đánh giá ảnh hưởng, đánh giá rủi ro - Bổ sung KMS cho tra cứu các hướng dẫn liên quan CR, CM | Change Management, Development team, CAB, PQA
17 | Change Management | Communication Plan chưa có hướng dẫn cụ thể | HIGH | - Team giao tiếp ad-hoc (không có quy trình) - Thông tin không nhất quán giữa các team - Rủi ro ảnh hưởng đến uy tín do phối hợp truyền thông đến KH | - Xác định các nhóm đối tượng cần thông báo (stakeholder groups) - Lên lịch thông báo: trước/trong/sau thay đổi (pre/during/post-change) - Ghi nhận thành tài liệu | Change Management Team, Product team, PQA
18 | Change Management | CAB thiếu quy định tiêu chí đánh giá & họp định kỳ | HIGH | - Thiếu tiêu chí đánh giá ổn định có thể dẫn tới quyết định của CAB không nhất quán - Không có tracking định kỳ | - Xác định tiêu chí đánh giá chính - Xác định lịch họp CAB định kỳ - Ghi nhận decision log | Change Management Team, CAB
19 | Change Management | RACI chưa có tài liệu chính thức | HIGH | - Không rõ trách nhiệm và quyền hạn, có thể gây xung đột trong quyết định CM - Khó Audit | - Ban hành bổ sung RACI - Có cơ chế cập nhật khi phát sinh thay đổi | Change Management Team, PQA
20 | Change Management | Change Failure Request (CFR) Root Causes chưa có phân tích chiến lược | HIGH | Không hiểu nguyên nhân gốc của các request Fail sẽ khó improve | Phân tích top 3 nguyên nhân gốc của các CFR để có kế hoạch cải thiện | Change Management Team, Development team, PQA
21 | Change Management | Incident-Change Linkage thực hiện manual | HIGH | - Incident investigation cần truy vết thủ công - Effort cao, thời gian xử lý (TAT) chậm | - Xây dựng query tự động hóa liên kết incident-change - Tích hợp API - Test tự động hóa & đào tạo team | Change Management Team, Incident Management Team, Development team, PQA
22 | Change Management | CMDB Integration chưa thiết lập | HIGH | - Không biết thay đổi ảnh hưởng những cấu hình nào - Không track dependencies giữa các CIs - Khó phân tích nguyên nhân gốc (root cause analysis) | - Xác định các CIs chính yếu (core CIs) - Ánh xạ Change Request với CIs - Tích hợp CMDB với Jira - Tự động cập nhật khi deployment | Change Management Team, Development team, Infra
23 | Change Management | Sonar đang tạm dừng hoạt động | HIGH | Quality control yếu | - Restart lại Sonar | Trao đổi thêm với Devops
24 | Change Management | PIR chưa kết nối CI/CD, kiểm tra manual | MEDIUM | - Không biết PIR có match với deployment thực tế Không - Không track Tự động success metrics | - Tự động hóa kết nối giữa Jira & deployment tools - Tạo PIR success metrics - Tự động kích hoạt PIR khi deploy | Change Management Team, DevOps Team, VHUD
25 | Change Management | Maintenance Window chưa có quy định criticality-based | MEDIUM | - Truyền Thông Không đồng nhất - Khách hàng Không biết lịch maintenance | - Định rõ chính sách maintenance window theo criticality (P1/P2/P3) - Tạo template thông báo - Cập nhật SLA | Change Management Team, DevOps Team, VHUD
26 | Change Management | Change Freeze Periods chưa có quy định cụ thể | MEDIUM | Ảnh hưởng Sprint Planning | - Tạo chính sách freeze period - Thông báo 30 ngày trước (advance notification) - Truyền thông lịch hàng quý - Tích hợp vào sprint planning | Change Management Team, Development Team
27 | Change Management | Dashboard chưa tự động lấy dữ liệu theo thời gian chọn | MEDIUM | - Lãnh đạo Không có data real-time để quyết định - Tracking SLA Không chính Xác | - Xây dựng tự động hóa dashboard (API/query) - Thêm date picker để chọn khoảng thời gian - Xuất bản hàng tuần/tháng - Setup real-time alerts | Change Management Team, BI team?
28 | Change Management | Batch Approval cho nhóm change liên quan chưa có | MEDIUM | - Approval process Không tối ưu | - Ánh xạ services với hệ thống hiện tại - Nhóm changes theo service - cập nhật batch Approval workflow - Test quy trình | Change Management Team, Service Owner, Infra, Development Team
29 | Change Management | Feedback & Improvement chưa có backlog cụ thể | MEDIUM | Chưa có roadmap cho cải thiện nên chưa có hiệu quả | - Tạo template improvement backlog - Review hàng tháng với team - Ưu tiên theo tác động (impact) & nỗ lực (effort) - Theo dõi hoàn thành | Change Management Team, ITSM lead
30 | Change Management | Training CM chưa đặc thù & chuyên sâu | MEDIUM | Chưa có training cho CM, chủ yếu tự học | - Thiết kế training CM chuyên sâu (ITIL 4 Practice) | Change Management Team, ITSM lead, L&D, HR
31 | Change Management | Chứng chỉ & yêu cầu năng lực CM chưa định rõ | MEDIUM | - Không có Kế hoạch tuyển dụng - rủi ro Mất nhân tài, năng lực Không scale | Xây dựng 4P next gen cho CM | ITSM lead, HR
32 | Configuration | Chính sách CMDB chưa formal | CRITICAL | Không rõ scope, CI types, roles → quản lý không nhất quán | Tạo CMDB Policy Charter document
33 | Configuration | Không có tool CMDB - sử dụng Excel | CRITICAL | Không thể tự động, không relationship mapping, không integration | Đánh giá & select CMDB tool (ServiceNow/Remedy)
34 | Configuration | Chưa map CI relationships & service dependencies | HIGH | Không biết service nào phụ thuộc CI nào → không tính impact được | Map service-to-CI cho top 10 services
35 | Configuration | Không có audit trail & audit process | HIGH | Không track thay đổi (ai, khi nào) → rủi ro compliance | Setup audit logging, monthly audits
36 | Configuration | CI Owners không được gán rõ ràng | HIGH | Không ai chịu trách nhiệm keep data accurate → dữ liệu lỗi thời | Gán CI Owner cho mỗi hệ thống
37 | Configuration | Không có CMDB Steward role & governance | HIGH | Không ai quản lý tổng thể CMDB, conflicts không resolve | Assign CMDB Steward
38 | Configuration | CMDB không integrate Incident & Change | HIGH | Incident/Change workflows không dùng CMDB data → không update | Integrate CMDB with tools
39 | Configuration | Không có data quality standards | HIGH | Duplicate CIs, inconsistent data → không tin tưởng CMDB | Define quality standards, validation
40 | Configuration | Không có auto-population từ monitoring tools | MEDIUM | Manual data entry → thời gian lãng phí, data lag | Setup data feeds từ monitoring tools
41 | Configuration | CMDB team part-time, không training | MEDIUM | CMDB không ưu tiên, team burnout, knowledge loss | Assign dedicated CMDB Admin, provide training
42 | Configuration | Không có KPI đo CMDB effectiveness | MEDIUM | Không biết coverage, quality → không justify investment | Define metrics, create dashboard
43 | Process QA | NO audit checklists (IM, CM, PM) | CRITICAL | Audits ad-hoc, inconsistent | Create standardized checklists
44 | Process QA | Audit frequency yearly only | CRITICAL | Cannot identify trends | Plan quarterly audits
45 | Process QA | Coverage only 3% (1/30 processes) | CRITICAL | Most processes never audited | Create 3-year plan for 80% coverage
46 | Process QA | Metrics almost ZERO (10%) | CRITICAL | Cannot measure PQA effectiveness | Define & track 5 key metrics
47 | Process QA | NO escalation for critical findings | CRITICAL | Critical issues ignored | Define escalation procedure
48 | Process QA | NO maturity assessment | MEDIUM | Cannot prioritize improvements | Use maturity framework (ITIL)
49 | 3rd party Management | NO formal 3PM Policy | CRITICAL | Write formal policy, CIO approve
50 | 3rd party Management | NO Vendor Classification | CRITICAL | Create critical/high/medium/low matrix
51 | 3rd party Management | NO SLA Monitoring | CRITICAL | Setup SLA dashboard, weekly reports
52 | 3rd party Management | NO Vendor Metrics | CRITICAL | Define & track 5-7 KPIs per vendor
53 | 3rd party Management | NO Risk Assessment | HIGH | Define risk assessment framework
54 | 3rd party Management | NO Roles & Authority | HIGH | Document vendor manager roles
55 | QC | Không có chiến lược và roadmap QC rõ ràng | CRITICAL | Thiếu định hướng dài hạn, không thể đo lường tiến bộ, không liên kết với mục tiêu kinh doanh | Xây dựng QC Strategy 3-5 năm với roadmap chi tiết, KPIs đo lường, và liên kết trực tiếp với business objectives
56 | QC | Không có quy trình test planning được chuẩn hóa | CRITICAL | Thiếu tính nhất quán, khó đảm bảo chất lượng test, không thể quản lý rủi ro hiệu quả | Thiết lập quy trình Test Planning chuẩn với template, timeline, và approval workflow rõ ràng
57 | QC | Chưa có metrics và KPIs cho QA/QC | CRITICAL | Không thể đo lường hiệu quả QC, không có cơ sở để cải tiến, không thể chứng minh giá trị | Thiết lập bộ KPIs QC core (Test Coverage, Defect Density, Automation Rate, etc.) với targets và dashboards
58 | QC | Không đo lường được test coverage | CRITICAL | Không biết được mức độ test đầy đủ, rủi ro cao về untested code, không thể tối ưu effort | Triển khai công cụ đo coverage (code coverage, requirement coverage) và thiết lập target tối thiểu
59 | QC | Không có chiến lược test automation | CRITICAL | Automation không có hướng đi rõ ràng, lãng phí resources, ROI thấp | Xây dựng Test Automation Strategy với roadmap, tool selection, training plan, và ROI targets
60 | QC | Không có quy trình test data management | CRITICAL | Test data không đáng tin cậy, rủi ro bảo mật cao, tốn thời gian setup manual | Thiết lập Test Data Management strategy với data provisioning, masking, và governance process
61 | QC | Không tuân thủ các chuẩn QC quốc tế | CRITICAL | Không đáp ứng yêu cầu compliance, khó đối chiếu với best practices, rủi ro trong audit | Áp dụng framework chuẩn (ISTQB, ISO 29119) và thiết lập traceability từ requirements đến test results
62 | QC | Quy trình Defect Management không được chuẩn hóa | HIGH | Bugs không được xử lý nhất quán, khó prioritize, không có accountability | Chuẩn hóa Defect Management process với priority/severity matrix, SLA theo mức độ, và workflow rõ ràng
63 | QC | Quality gates không được thực thi đầy đủ | HIGH | Code quality không được đảm bảo, bugs có thể leak sang production | Thực thi quality gates nghiêm ngặt: build fail khi test fail, mandatory test coverage checks
64 | QC | Chỉ có 1 test environment, không có configuration management | HIGH | Bottleneck trong testing, conflicts giữa các team, không thể test parallel | Thiết lập multiple test environments (Dev, SIT, UAT) với automation provisioning và config management
65 | QC | Chính sách QC chỉ ở mức high-level và hiếm khi được cập nhật | MEDIUM | Chính sách không đủ chi tiết để hướng dẫn thực thi, không theo kịp thực tế | Phát triển QC Policy riêng biệt, chi tiết hơn với cơ chế review định kỳ (6 tháng/lần)
66 | QC | RACI matrix không được tài liệu hóa | MEDIUM | Thiếu clarity về trách nhiệm khi có thay đổi team hoặc escalation | Tài liệu hóa RACI matrix cho tất cả QC activities và update định kỳ
67 | QC | Quy trình regression testing không rõ ràng | MEDIUM | Edge cases không được cover, rủi ro regression bugs | Chuẩn hóa regression testing process, tăng automation coverage, bao gồm edge cases
68 | QC | Performance testing chỉ làm theo yêu cầu, không có benchmarks | MEDIUM | Performance issues có thể không được phát hiện sớm, không có baseline để so sánh | Thiết lập performance benchmarks và làm load testing định kỳ cho critical systems
69 | QC | Skill gaps đáng kể và không có training có tổ chức | MEDIUM | Team capability không được phát triển, phụ thuộc vào self-learning | Thiết lập training program có cấu trúc với focus vào automation, test design, và domain knowledge
70 | QC | Không có defect triage process định kỳ | MEDIUM | Bugs resolution có thể chậm, thiếu forum để discuss technical issues | Thiết lập defect triage meetings định kỳ (weekly) giữa QC và Dev
71 | QC | Không có test execution reports | MEDIUM | Stakeholders không có visibility về test progress và quality status | Thiết lập automated test reporting với key metrics và trends
72 | QC | Tỷ lệ team biết automation tools thấp (25-30%) | MEDIUM | Automation không scale được, phụ thuộc vào một số người | Training toàn bộ QC team về automation tools, thiết lập automation champions
73 | QC | Không có release testing process, rollback plan không chi tiết | MEDIUM | Rủi ro cao khi release production, không có safety net | Thiết lập release testing phase với checklist và rollback plan chi tiết
74 | QC | Không có quy trình continuous improvement và roadmap nâng cao capability | MEDIUM | QC capability không được cải thiện có hệ thống | Thiết lập continuous improvement process (retrospectives, lessons learned) và maturity roadmap
75 | QC | Không rõ về tuân thủ GDPR và data protection trong testing | MEDIUM | Rủi ro compliance với data protection regulations | Đánh giá compliance gap và thiết lập data protection controls cho test data

## Timeline Overview
Phase | Thời gian | Focus | Key Deliverables
Phase 1: Foundation & Quick Wins | Tháng 1-3 | Thiết lập nền tảng, xử lý CRITICAL | RACI, SLA, Audit checklists, 3PM Policy
Phase 2: Process Maturity & Integration | Tháng 4-6 | Nâng cao quy trình, tích hợp | CMDB tool, Integrated processes, QC strategy
Phase 3: Automation & Optimization | Tháng 7-9 | Tự động hóa và tối ưu | Automated workflows, Test automation, Auto-discovery
Phase 4: Compliance & Improvement | Tháng 10-12 | Tuân thủ và cải tiến liên tục | Compliance cert, Maturity assessment, Training program

## Top Priority Actions
STT | Area | Finding | Action | Owner
1 | Request fullfilment Management | Metrics not tracked (SLA %, cycle time) | Setup dashboard tracking 5 key metrics
2 | Request fullfilment Management | NO quality & CSAT measurement | Create CSAT survey, quality metrics
3 | Request fullfilment Management | Weak ITSM integration (all manual) | Auto-link incidents/changes, CMDB update
4 | Request fullfilment Management | NO formal service review | Setup monthly review with bottleneck analysis
7 | Incident | Incident Manager role not defined | Define & assign Incident Manager role + responsibilities
8 | Incident | SLA not approved per severity (P1-P4) | Define SLA per severity, get approval
9 | Incident | Escalation path ad-hoc, not formal | Create escalation matrix by severity/type
11 | Incident | ITSM integration 0% (Problem/Change/CMDB) | Integrate incidents with Problem/Change/CMDB
13 | Change Management | Phân tích rủi ro chưa có thang đánh giá và phân loại | - Tạo thang đánh giá rủi ro 1-5 - Xác định các tiêu chí thay đổi cao rủi ro - Tạo đường dẫn escalation (escalation path) - Ghi nhận thành tài liệu | Change Management, CAB team, PQA
14 | Change Management | Chưa có quy định về lưu trữ và backup dữ liệu CR | - Định rõ chính sách lưu giữ (thời hạn lưu trữ, theo iTIL thì 1-3-5 năm tùy theo Tier, ISO 27001: 5 năm) - Tạo quy trình sao lưu hàng tháng - Test quy trình khôi phục (restore) | Change Management, Infra
15 | Change Management | Chưa triển khai Audit đối với hoạt động CM | - Lên lịch compliance audit - Xác định phạm vi audit & danh sách kiểm tra (checklist) - Ghi lại các vi phạm & Kế hoạch khắc phục | Change Management, PQA
32 | Configuration | Chính sách CMDB chưa formal | Tạo CMDB Policy Charter document
33 | Configuration | Không có tool CMDB - sử dụng Excel | Đánh giá & select CMDB tool (ServiceNow/Remedy)
43 | Process QA | NO audit checklists (IM, CM, PM) | Create standardized checklists
44 | Process QA | Audit frequency yearly only | Plan quarterly audits
45 | Process QA | Coverage only 3% (1/30 processes) | Create 3-year plan for 80% coverage
46 | Process QA | Metrics almost ZERO (10%) | Define & track 5 key metrics
47 | Process QA | NO escalation for critical findings | Define escalation procedure
49 | 3rd party Management | NO formal 3PM Policy
50 | 3rd party Management | NO Vendor Classification